## Sheet1
Priority 1 - Custom Country Timeline | Weeks
| Development |  |  |  | Testing |  | Deployment
Roles | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 - SIT | Week 6 - UAT | Week 7 | Week 8 | Total hours
Full Stack Developer | 10 | 10 | 15 | 15 | 10 | 5 | 5 | 5 | 75
Senior Backend developer (Dataiku) | 20 | 20 | 20 | 20 | 20 | 5 | 5 | 5 | 115
Tester |  |  | 10 | 10 | 20 | 5 | 5 | 5 | 55
Total | 30 | 30 | 45 | 45 | 50 | 15 | 15 | 15 | 245
Priority 2.3 and 2.4 - Code Studio and API Designer | Weeks
| Development |  |  | Testing |  | Deployment
Roles | Week 1 | Week 2 | Week 3 | Week 4 - SIT | Week 5 -UAT | Week 6 |  |  | Total hours
Full Stack Developer | 20 | 20 | 20 | 10 | 5 | 10 |  |  | 85
Senior Backend developer (Dataiku) | 20 | 20 | 20 | 20 | 5 | 10 |  |  | 95
Tester |  | 10 | 10 | 20 | 5 | 4 |  |  | 49
Total | 40 | 50 | 50 | 50 | 15 | 24 |  |  | 229
Priority 3 - Migration Efficiency | Weeks
| Development |  | Testing |  | Deployment
Roles | Week 1 POC | Week 2 -Dev | Week 3 - SIT | Week 4 - UAT | Week 5 |  |  |  | Total hours
Full Stack Developer | 20 | 30 | 10 | 10 | 10 |  |  |  | 70
Total | 20 | 30 | 10 | 10 | 10 |  |  |  | 70