## Sheet1
Phase | Estimated Hours
I. Frontend Migration & Refactoring (React in Code Studio) | 85
- Setup project structure in Code Studio | 10
- Refactor existing frontend codebase to meet Code Studio standards | 25
- Update API integration calls for compatibility with API Designer | 20
- Modify environment configs & secrets handling for DataIKU | 15
- Implement required UI fixes post-migration | 15
II. Backend Migration & Refactoring (API Designer - Flask + DataIKU) | 95
- Setup API Designer project & environment | 15
- Refactor existing Flask APIs to align with API Designer | 25
- Update database connectors (PostgreSQL/Redshift) in API Designer | 20
- Implement changes for authentication & environment variables | 15
- Regression fix for migrated APIs | 20
III. Integration & Validation | 20
- Validate Code Studio (frontend) to API Designer (backend) connectivity | 10
- Update deployment pipelines for SIT & UAT environments | 10
IV. Testing | 49
- Unit testing for frontend migration changes | 8
- API testing for migrated endpoints | 10
- Integration testing (Frontend + Backend + DB) | 12
- Regression testing post-migration | 7
- SIT Testing Support | 6
- UAT Testing Support | 6
V. Deployment | 24
- Code review & refactoring adjustments | 5
- SIT deployment & validation | 7
- UAT deployment & validation | 7
- Final Production Deployment | 5